## Project Status (hidden)
Project Status Report
Project: |  |  | BVI Loan Fund |  |  |  | 2015-10-16
CTR Sponsor: |  |  | Anna Jones (Rosanne for VLE Foundation) |  |  | Overall Status: | G
Project Manager: |  |  | Toby Abbott (Elena for VLE Foundation)
Progress Summary
Progress Summary: |  |  | Unite Board agreed to funding for Foundation and Fund Governance and management structure agreed in principal with VLE, VP Bank and Harneys KPMG and BCoEC in final stages of contract to deliver parallel programme to support entrepreneurs in BVIs Foundation Manager and Ops Manager recruited Commenced setting up Foundation entity
Next Steps: |  |  | Finalise and set-up Foundation structure ahead of Foundation Manager starting On-board Foundation and Operations Manager Support KPMG / BCoEC partnership MOU or SLA with key stakeholders Financial modelling of fund Identify potential 24902 Community involvement with Suse Branding and positioning Support VLE with governance and objectives assessment for Foundation
Project Management Summary
Governance |  | G | Harneys have outlined an inititial goverance framework; VLE to set up Foundation, under which loand fund will sit.
Progress |  | G | Aiming for first loans in February 2016
Scope |  | G | Scoping conversations well underway with all parties - MOU/SLA next step
Costs |  | G | Loan fund size agreed at $200,000. CapEx and OpEx budget agreed internally.
Resources |  | G | Foundation Manager to be employed by VLE and 50% funded by Unite.
Benefits |  | G
Engagement |  | G
Functional Summary
Legal |  | A | No official agreements in place yet. MOU/SLA as first step.
Finance |  | G
Communications |  | A | Need comms plan for launch
Brand |  | A | Need to set up brand meeting internally at VLE (include Jonno?)
People |  | N/A
Top Issues
# | Issue Title |  | Issues Description and Impact | Priority | Resolution | Owner | Target Date
1
2
3
Top Risks
# | Risk Title |  | Risk Description and Impact | Risk Score | Mitigation | Owner | Target Date
1 | KPMG/BCoEC partnership falls through |  | If KPMG/BCoEC partnership doesn't materialise, we will need extra on-island marketing for fund | Low | Continue to work with KPMG and BCoEC to clarify mutually beneficial partnership | Toby | 2015-08-31
2 | Failure to get all party agreement |  | BVI Loan Fund requires agreement and co-operation from a number of parties. Any disagreement could derail the project. | Low | Draw up SLA or MOU to confirm roles and responsibilities | Toby | 2015-08-31
3 | Timescales |  | It takes longer than expected to recuit VLE Foundation Manager and set up Foundation leading to project delays | Med | Support VLE with progress | Elena/Toby | 2015-08-31
Impact Metrics (Quality) Dashboard
N/A until project launch

## Project Summary (hidden)
Project Summary
Project: |  | BVI Loans
Project Sponsor: |  | Anna Jones
Project Manager: |  | Toby Abbott
Project Description |  |  | Project Team
The BVI Loan fund is a project to set up a loan programme in the BVIs using $200,000 intitial investment from Richard Branson and Larry Page. The first phase of the scheme will be delivered in partnership with KPMG who will provide a pipeline of business plans that need debt finance to be reviewed by an investment committee. Project to cover period up until first loans are made before handing over to business as normal operations. Learning and mentoring aspect of loan fund to be delivered by BCoEC Fund management by VLE Foundation
Major outcomes / benefits / impacts
1 | Entrepreneurs in BVIs with limited access to capital have option of debt finance
2 | BVI entrepreneurs set up businesses in underserved areas
3 | BVI entrepreneurs set up businesses that employ local people and add to local economy
4 | BVI entrepreneurs set up businesses that have a positive people and planet impact
Top Level Plan
Business Case Overview

## CBCA Project Vision
[CITY NAME] CBCA Project Vision
Vision
Please explain your vision for a local climate alliance/partnership between the city and businesses, and how you expect it will advance the city's climate goals. | [ANSWER]
Existing Connections and Programming
Which businesses in your city do you currently engage most with? Which do you engage least with/ not engage at all? (Why/ why not?) | [ANSWER]
What's the nature of the existing city-business relationships? e.g. network at conferences, policy consultations, ongoing relationship with a group of suppliers, market dialogue around procurement, forum of leading local businesses | [ANSWER]
Who in each city department is working with which (type of) private sector actors? | [ANSWER]
Which allies can you lean on in the city to do this work with you locally? e.g. Green Building Councils, Professional (e.g. architects’) associations | [ANSWER]
Policy and Influence
What kind of policies do you have to incentivise (or disincentivise) certain practices by private sector actors? e.g. building area bonuses or expedited permitting for green building approaches, leadership platform or awards programme with visibility/ reputational benefits, building standards to promote low-carbon, circular material use | [ANSWER]
Desired Outcomes
Which specific issues would you like to tackle in collaboration with local businesses to accelerate building decarbonisation? | [ANSWER]
How do you envision a successful city-business partnership on building decarbonisation would look in 2 years time? What outcome (ambitious yet feasible) do you aim to achieve through city-business engagement? | [ANSWER]
Leadership
Is the Mayor or another member of your citys leadership committed to working with the local business community and other stakeholders on building decarbonisation? | [ANSWER]
Are there any civic leaders in your city that you can lean on to help you develop a climate partnership? e.g. philanthropy directors, politicians, vocal business leaders etc. | [ANSWER]
Resources
What resources do you need to deliver the project? In terms of time commitment from city staff, what level of resourcing would your City be able to devote to this initiative? | [ANSWER]
Activities
What activities do you propose to develop your City-Business Climate Alliance? | [ANSWER]

## CBCA Project Plan
Developing a City-Business Climate Alliance: Project Plan Template
Start Date: | 2026-01-01
[5 empty] | Y1 | [11 empty] | Y2
Phase | Activity | Details | Deadline | Status | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
Set-up phase (Year 1) | Identify main responsible person(s) | Identify a person within the city government to set up the Alliance. Think carefully about the seniority and department(s) of the person who will lead the project in this first phase. | 2026-01-01 | bar: Y1 M1
| Develop a Project Plan | Develop a high-level project plan, including objectives, timeline, who to involve, key outputs and deliverables. | 2026-01-01 | bar: Y1 M1
| Kickoff Meeting to set project scope |  | 2026-01-01 | bar: Y1 M1 to Y1 M2
| Conduct desk research on ecosystems + existing city business partnerships | Research city contexts and ecosystems to build a profile based on the City's Cliamte Action Plan Review existing city business partnerships to identify options in terms of governance and business models (governance model to be adapted to cities's needs and preferences) | 2026-03-02 | bar: Y1 M1 to Y1 M2
| Conduct a needs assessment | Assess the existing structures, budget, inter-departmental links, legal constraints, etc., maturity assessment, stakeholder map (incl. possible local convening partners e.g. Regional Hubs, Chambers of Commerce, etc.) and related comms guidelines, business landscape and rules of engagement with private sector (dependent on local regulations) | 2026-03-02 | bar: Y1 M1 to Y1 M2
| Set up and faciliate core working group | Set up a core working group that will meet 1-2 times per month. The group should include representatives from relevant departments e.g. climate team, economic development team. You may also include othe co-founding organisations in the working group e.g. a local university, core philanthropic funder. Decide on main methods of communication e.g. email, Microsoft Teams channel, whatsapp group, monthly meetings | 2026-03-02 | bar: Y1 M1 to Y1 M2
| Organise 1-day online or in-person workshop with the working group to identify priorities and develop high level roadmap | Deliverables to include: high level targets + high level roadmap with short-, medium- and long-term strategy (incl. options for governance model, financing model, business model, implementation model and business onboarding plan) | 2026-04-01 | bar: Y1 M1 to Y1 M3
| Conduct business mapping exercise | Map the key businesses and organisations you want to target for your Alliance. Key things to consider when identifying and prioritising possible members: emissions data, climate commitments, CDP score, square foot of office or facility space, number of employees, revenue etc. | 2026-05-01 | bar: Y1 M3 to Y1 M4
| Develop value proposition for local businesses | Develop messaging and value proposition to engage business to join the Alliance | 2026-05-31 | bar: Y1 M3 to Y1 M5
| Select and onboard local businesses | Depending on the agreed strategy, use third party networks or chambers of commerce to help facilitate introductions. Consider sending invitations from the Mayor. | 2026-06-30 | bar: Y1 M4 to Y1 M6
| Organise high level launch with Mayor | Organise an in-person event to engage stakeholders at City level, and officially kick off CBCA programme of activities. This could include a formal commitment signing. | 2026-08-29 | bar: Y1 M5 to Y1 M8
| Agree formal commitments with business partners | Formal commitments to provide framework and direction for all future activities at city level, and build environment of trust for city officials and business representatives to work together | 2026-08-29 | bar: Y1 M7 to Y1 M8
| Set up working groups and review existing plans | Working groups to ensure the right experts are involved (both from the City administration and the business partners's teams), help divide the efforts into manageable workloads, and dive deeper in each area | 2026-11-27 | bar: Y1 M9 to Y1 M11
| Agree on a formal operating model, governnance structure and financial model | Agree on the formal operating model (how often will you meet, how will activities be organied etc.), governance structure (who makes decisions and how) and financial model (funding streams or in-kind resources) | 2027-01-01 | bar: Y1 M11 to Y1 M12
Implementation phase (Year 2) | Organise a series of workshops to draft workplan for each focus area | Workshops to include a co-creation process but also processes to identify solutions that may already exist and that can be trialled locally or, where possible, opportunities to adapt projects from others in the group | 2027-04-01 | bar: Y2 M1 to Y2 M3
| Develop detailed communications strategy | Comms strategy to include activities targeted at the general public and at policymakers/ private sector stakeholders (advocacy). Consider creating a social media page or private group | 2027-04-01 | bar: Y2 M2 to Y2 M4
| Secure finance for projects and to fund the city-business partnership in the long term | Start implementing financial model e.g. membership fees, or fundraise for specific projects | 2027-04-01 | bar: Y2 M2 to Y2 M4
| Put in place a reporting and monitoring system | Agree on a regular reporting framework (by the city and the companies) to help keep the group accountable to the established baselines, enabling a full and transparent assessment of progress over time. Data points for the monitoring can be collected through company disclosure to the city. This monitoring framework should rely on a baseline assessment taken at the start of the collaboration and run regular progress checks. (Example - tracking a commitment made by all companies in the Alliance to transition their fleets to 100% electric vehicles by 2030. Companies would report their baseline to the city and then track their progress against this goal on an annual basis). | 2027-04-01 | bar: Y2 M3 to Y2 M5
| Roll out communications strategy - Inform policymakers | City teams to engage with other policymakers as needed and depending on the city context. This may be local authorities within the city boundary, state or regional levels of government or the national government. This engagement can help push through changes in rules and regulations, national legislation and funding streams that can help the city meet its goals and, perhaps, encourage new climate-related policies and spur the expansion of other City-Business Climate Alliances. | 2027-04-01 | bar: Y2 M4 to Y2 M6
| Conduct regular evaluation and adaptation | Based on the agreed reporting and monitoring system (see above) | 2027-04-01 | bar: Y2 M12
| Hold annual high-level strategic meeting | Annual strategic meeting to ensure engagement and commitment of high level stakeholders at city level and among the business partners (e.g. Mayor and CEOs) and review the strategic direction of the local city-business partnership | 2027-04-01 | bar: Y2 M12
| Agree strategy to scale | Strategy to be implemented from Year 3, depending on advancement of local activities | bar: Y2 M11 to Y2 M12
Expansion phase (year 3) | Scale (detail TBC) | Expansion based on strategy agreed in year 2, both locally (e.g by increasing number of businesses / sectors / focus areas / initiatives at city level, or by involving supply chains) or on a regional / national level support to other cities in implementing the CBCA model (e.g. if some of the businesses involved tend to operate on a regional / national level)
| Conduct studies on cost abatement? | TBC
| Implement projects | Based on the agreed implementation strategy, reviewed regularly according to monitoring and evaluation activities
| Conduct regular evaluation and adaptation | Same as Year 1
| Hold annual high-level strategic meeting | Same as Year 1
| Develop knowledge sharing materials for CBCA global network | Exact contribution TBC with Alliance partners

## Project Plan (hidden)
# | Task | 2014-11-01 | 2014-12-01 | 2015-01-01 | 2015-02-01 | 2015-03-01 | 2015-04-01 | 2015-05-01 | 2015-06-01 | 2015-07-01 | 2015-08-01 | 2015-09-01 | 2015-10-01 | 2015-11-01 | 2015-12-01
1 | Reach MOU with KPMG
2 | Scope governance arrangements
3 | Scope loan administration arrangements
4 | Scope brand arrangements
5 | Finalise Scope, Cost and Plan
6 | Agree with Jean
7 | Pitch to Richard
8 | Finalise governance arrangements
9 | Finalise Loan Adminstration arrangements
11 | Set up Investment Committee
12 | Review first batch of loans
13 | Adminstor first loans

## ISSUES (hidden)
# | Issue Title | Issues Description and Impact | Priority | Resolution | Owner | Target Date
1
2
3
4
5
6
7
8
9
10
11
12

## RISKS (hidden)
# | Risk Title | Risk Description and Impact | Risk Score | Mitigation | Owner | Target Date
1 | KPMG/BCoEC partnership falls through | If KPMG/BCoEC partnership doesn't materialise, we will need extra on-island marketing for fund | Low | Continue to work with KPMG and BCoEC to clarify mutually beneficial partnership | Toby | 2015-08-31
2 | Failure to get all party agreement | BVI Loan Fund requires agreement and co-operation from a number of parties. Any disagreement could derail the project. | Low | Draw up SLA or MOU to confirm roles and responsibilities | Toby | 2015-08-31
3 | Timescales | It takes longer than expected to recuit VLE Foundation Manager and set up Foundation leading to project delays | Med | Support VLE with progress | Elena/Toby | 2015-08-31

## Data (hidden)
High | 2014-07-01 | R
Med | 2014-08-01 | A
Low | 2014-09-01 | G
None | 2014-10-01 | N/A
2014-11-01
2014-12-01
2015-01-01
2015-02-01
2015-03-01
2015-04-01
2015-05-01
2015-06-01
2015-07-01
2015-08-01
2015-09-01
2015-10-01
2015-11-01
2015-12-01
2016-01-01
tbc